## Instructions
Enhanced RACI Technique
Presented by Thea Soehren https://www.linkedin.com/in/TheaSoehren/
RACI is an acronym -
Responsible – These are the people who will do the work.
Accountable – This is the ONE person who will be sure the task is completed.
Consulted (before the event) - This person wants to have a say in some aspect of the event – it is best to note what specifically they want to be involved so you bring them in at the right time.
Informed (after the event) - This person wants to be told when some portion of the event has happened (and may want to also receive information about the results). – it is best to note what specifically they want to be informed of so its easy to remember what to send them.
Stage 1 – Planning and Agenda
1. Identify your Goal, What is in Scope and What is out of Scope.
2. Think about what they need to be told before the meeting to orient them to the situation and the goals of the meeting (details, set the stage, etc.).
3. Create your RACI in a shared location; Ideally, a platform that will send a notification when updates are made to the document.
4. Craft your email / meeting invitation.
Stage 2 – Meeting Beginning
1. Beginning the meeting, tell the participants you will be using a RACI to track the decisions and tasks identified.
2. Explain the RACI acronym (above).
3. Explain the results of this meeting will all be recorded on the RACI, including the resolution of each task.
4. Explain the RACI will be sent out to "all impacted parties, the meeting participants and others interested in this meeting." They will hear - pay attention - this is recorded and others will know what you agree to!
5. Show them their names across the top - because their input is valuable.
6. Keep the RACI on the screen during the meeting so they can see their contributions recorded and they can speak up to make corrections if needed.
7. If anyone joins the meeting, stop and make a point of adding their name to the top (confirm they are familiar with RACI and provide instructions if needed).
Stage 3 – Conduct Meeting/RACI
1. Present the topics in order of most important to least.
2. Record the tasks with the category listed in front to keep it together.
3. Be VERY SPECIFIC as to what is being discussed - always look at it to be sure someone not in the meeting would completely understand what you are talking about by what is written.
4. With each task, ask – who wants to be involved (not who is leading), and record R in those. When you get enough people for that task, ask those who are identified as R “which of you want to lead this endeavor?” and change the “R” to “R/A” – be sure you have only ONE A per task.
5. Ask those Responsible the Responsible/Accountable people, when this decision or task will be completed, and add this information to the Date/Time Due column.
6. Have a calendar ready so you can specific the date and time (by 10 am or EOD is fine) – ask THEM to provide the date, and if you don’t also get a time, suggest a time, like “Is EOD fine?” and wait for their answer.
7. Then after you get the R and A, ask “Is there anyone who wants to be consulted about this task before the decision or action?” and record those people with C. ALSO ask what specifically they want to be consulted about, and add that to the same square.
8. After you ask about being Consulted, ask “Is there anyone who wants to be informed about this task after the decision or action?” and record those people with I. ALSO ask what specifically they want to be informed about, and add that to the same square.
9. Put in the email address, distribution address or share point folder things are to be submitted / sent.
a. If there is someone to receive this information, or a dependent task, ask them if that date will work; sometimes they may say they will need the information a few days earlier and then you let them have that discussion/you make changes to the date/time as needed.
10. Take suggestions immediately even if you only record the idea(s) to talk about later.
11. As you hear decisions being made - make it a point of documenting the decision and asking if each person agrees - document the agreement or disagreement in their column. If you have disagreement - ask the team if further discussion will be needed or if the one to make the final decision is present - make the notes for next steps.
Stage 4 – Meeting Wrap up
After all categories have been discussed, decisions agreed to, and responsibility/involvement indicted:
1. Review the tasks by category to be sure nothing was left out, dates work, etc. - make updates as needed.
2. As you touch on each task, note the Accountable person (or their delegate) shall be entering the resolution and appropriate link to the resolution document into the Resolution column. This makes is easy to see which items are closed or still open.
3. Within each category, mention the decision made, but you don't need to go deeper into the decisions.
4. Then review all of the tasks by PERSON and ask at the end "Can you handle this with these dates?"
5. If someone has stepped out of the meeting, indicate they have not agreed by making their column a different color - after the meeting YOU go review their column with them and when they agree (or make changes), change the color back to normal.
Stage 5 – Send Out and Post
1. After verifying with anyone who had to step out of the meeting, send out a meeting minutes email ASAP with a link to the RACI.
2. It’s a very good idea to explain the RACI acronym with this email.
Stage 6 – Follow up / Update
1. As items are coming up on the date due, if you don't see they are completed, approach the person asking if they are on track. They may be overloaded and may need to delegate.

## Template
Goal / Focus of Meeting: | Department Outing - Cowboy Ranch - Friday, March 21st, Friday, 9-5
Scope of Meeting: | Determine: Communication, Transportation, Games, Food, What Else?
Out of Scope: | 50 people (list confirmed and participant waivers signed & received), Destination Identified and paid, Event Budget Allocated: Unlimited, Date/Time 03/21, 9-5, Leaving from and returning to office (employee parking lot)
Task / Decision | Date /Time Due | Received by WHOM Via (method) | Notes / Next Successor | Resolution

## Example 2025-02-15
Goal / Focus of Meeting: | Department Outing - Cowboy Ranch - Friday, March 21st, Friday, 9-5
Scope of Meeting: | Determine: Communication, Transportation, Games, Food, What Else?
Out of Scope: | 50 people (list confirmed and participant waivers signed & received), Destination Identified and paid, Event Budget Allocated: Unlimited, Date/Time 03/21, 9-5, Leaving from and returning to office (employee parking lot)
Task / Decision | Date /Time Due | Received by WHOM Via (method) | Notes / Next Successor | Resolution | Amarachi | Rob Cor | Karishma | David | Cynthia
[5 empty] | Finance | Health and Safety
Communication - Intitail Communication | 2/19 - EOD | distro list |  |  |  | R/A |  |  | R
Communication - create distro list/test | 2/18 - Noon |  |  |  |  | R/A |  |  | R
Communication - Reminder Email | 3/6/2025 - EOD | distro list |  |  |  | R/A |  |  | R
Communication - Final Email | 3/17 - EOD | distro list |  |  |  | R/A |  |  | R
Transportation - Arrange Bus, Identify the Route, | 2/26 - EOD |  | To Communication - ROB@co.com: Location of depatture, arrival time for departure |  | I - contract to AMAR@co.com | C - H&S - ROB@co.com I - communication - ROB@co.com | R | R/A
Transportation - the Transportation company will be responsible for loading and unloading people, supplies and equipment (food / games). |  |  |  |  | agree | agree | agree | agree | agree
Transportation - the Transportation company will be responsible for providing the standard list of medical supplies for the busses. |  |  |  |  | agree | agree | agree | agree | agree
Transportation - loading will begin 45 min before departure (from each location) |  |  |  | NA | agree | agree | agree | agree | agree
Transportation - the Transportation company will be responsible for providing backup transportation if needed. |  |  |  | NA | agree | agree | agree | agree | agree
Transportation - Arrange for check in checklist of participants | 2/26 - EOD |  | To Communication - checklist plan for buses |  |  | I - communication - ROB@co.com | R | R/A
Transportation - particpants can choose to transport themselves (not ride the bus) |  |  |  | NA | agree | agree | agree | agree | agree
Transportation - particpants who choose to transport themselves will not be reimbused or funded. |  |  |  | NA | agree | agree | agree | agree | agree
Checklist at the venue - for those driving themselves. | 2/26 - EOD |  | To Communication - checklist for those driving themselves. |  |  | I - communication - ROB@co.com | R | R/A
Venue - Check conditions ahead of time | 2/18 - EOD |  |  |  | I - conditions acceptable or not - AMAR@co.com | R/A
Venue - Confirm | 3/19 - EOD |  |  |  | I - conditions acceptable or not - AMAR@co.com | R/A
Transportation - particpants who choose to transport themselves will be responsible for arriving at the venue; but if they have issues they can call transport coordinator. |  |  | Communication - convey | NA |  | I - communication - ROB@co.com

## Calendar
2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21
15 | 1 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21

## email
FOCUS OF THIS MEETING: | Department Outing, Scheduled for Friday, March 21, 9-5
SCOPE OF THIS MEETING: | Determine and assign the details for: Communication Transportation Games Food (what else?)
Out of SCOPE (Decisions alredy in place): | Number of people: 50 people, deparment employees and family members
Participants (50 people) have all signed waivers and HR has the signed waivers
Event Budget: This event has an unlimited budget - approved and in place
Transportation: Leaving at 9am from the employee parking lot, circle drive Returning at 5pm to the employee parking lot, circle drive
Destination: Cowboy Ranch, located 30 min from the office, is under contract/paid
Details about Cowboy Ranch: | 30+ horses are available to ride
Instructors are on site to teach horsemanship
Trail rides (3 guides to 10 guests) will depart on the EASY Trail every hour from 10am until 3 pm
Trail rides (2 guides to 5 guests) will depart on the CHALLENGE Trail at 11am and 1pm.
Challenge Trail participants must pass a horsemanship test prior to departure.
Depending upon availaibity:
A roping demonstration may take place at 12:30 (after lunch)
Wigon rides may take place at 10am, 1pm, 2pm and 3pm